## Sheet1
WJUSD - Measure Y Capital Improvement - Group 1
LLB Method - PROJECT SCHEDULE |  | Updated: 9/15/2023 VP
RFP - 1st Advertisement | Tuesday, September 19, 2023 | Publish Daily Democrat/Quality Bidders/Builders Ex
RFP - 2nd Advertisement | Tuesday, September 26, 2023 | Publish Daily Democrat/Quality Bidders/Builders Ex
Mandatory Project Walk | Thursday, October 5, 2023 | 7:30AM PROMPT - Mandatory project walk - beginning @ CCHS (meet @ front of school), 14320 2nd St., Yolo, CA - remaining 5 schools thereafter (plan 1 hr per school)
Final day for RFI submissions | Wednesday, October 11, 2023 | Submissions submitted through email by 3PM
RFI responses (Addendum) | Wednesday, October 18, 2023 | Submission will be uploaded to District page by 3PM
Prequalification notices due | Wednesday, October 18, 2023 | All contractors must be registered w/WJUSD through CUPPCA and Quality Bidders
Submittal of proposals | Wednesday, October 25, 2023 | Proposals must be submitted by 12PM - 910 College St., Woodland, CA
Proposal reviews | Thursday, October 26, 2023 | 4 person review panel
Notification short listed bidders | Monday, October 30, 2023 | Notification via email
Interviews - short list bidders | Thursday, November 2, 2023 | Time/location TBD - Notification via email
Fee proposal/Interview Review | Thursday, November 2, 2023 | 4 person review panel
Post RFP Scores - District page | Wednesday, November 8, 2023 | WJUSD - District Page (Maintenace & Operations)
Anticipated Board Approval | Thursday, November 16, 2023 | Scheduled WJUSD Board Meeting
Notice of Award/Agreement Issuance | Monday, 20, 2023 | Notice and documents via email
First OAC Meeting |  | TBD