## Sheet1
Woodland Joint Unified School District Measure Y Capital Project Group 1
Requests for Information
Date Received | Contractor | Information Requested | Response From District | District Response Due On
2023-09-27 | Roebbelen | May we receive copies of the intended agreement/contract forms referenced as Attachment 3 (Preconstruction Services Agreement, LLB Agreement - Site Lease, Sublease, and Construction Services Agreement)? | To be provided after District accepts partner. | Wednesday, October 18th, 2023 3:00 p.m.
2023-09-27 | Roebbelen | The scope of the project includes both preconstruction and construction services. Page 2 of 17 notes the estimated performance period is nine (9) months (12/2023-8/2024). Attachment 2 Fee Proposal notes 9 months for General Conditions (construction). Page 2 of 17 notes the award of the project is anticipated for 11/16/23. Preconstruction services typically runs in advance of construction – may we ask the district to articulate when preconstruction services (thru GMP) should be anticipated to take place? | Performance period will start after DSA approval, estimated date of DSA submittal is January 2024. | Wednesday, October 18th, 2023 3:00 p.m.
2023-09-27 | Roebbelen | May we receive a schedule for the various design milestones (SD, DD, CD), and the estimated DSA submittal and approval dates? | Currently district is surveying each site. Once completed, updated schedule will be provided. | Wednesday, October 18th, 2023 3:00 p.m.
2023-09-27 | Roebbelen | Please confirm questions are due by 10/11 and by what time (if before 5 PM)? | Correct, 5 p.m. | Wednesday, October 18th, 2023 3:00 p.m.
2023-09-27 | Roebbelen | Please confirm the project walk through is 10/5 at 9 AM via Zoom, or if it will be in-person at the project site(s). If the latter, please provide meeting location and time. | In person. | Wednesday, October 18th, 2023 3:00 p.m.
2023-10-03 | GCCI INC | Please clarify this statement “The successful contractor shall not provide any pre-construction services or work that required a contractor’s license pursuant to Business and Professions Code section 7065 et. seq.” | Shall provide. | Wednesday, October 18th, 2023 3:00 p.m.
2023-10-03 | GCCI INC | Attachment 4 is missing from the documentation (Pre Construction, Site Lease & LLB Contract) Please provide. | Will be provided once a succesful contractor is approved by District. | Wednesday, October 18th, 2023 3:00 p.m.
2023-10-03 | GCCI INC | Please clarify what the correct Submittal requirement is; page 4 states 1 original and 3 hard copies, page 10 states 1 original and 4 hard copies, each with a digital copy as well. | One original, and 4 hard copies along with a digital copy (on a thumb drive) of the proposal must be submitted under sealed cover by no later than Due Date for Submittal of Proposals specified in Section III. | Wednesday, October 18th, 2023 3:00 p.m.
2023-10-09 | GCCI INC | What is the anticipated start dates/project schedules for these projects? | After DSA approval, estimated plans January 2024. | Wednesday, October 18th, 2023 3:00 p.m.
2023-10-09 | GCCI INC | Can we have 1 supervisor covering the projects on all sites? | Yes. | Wednesday, October 18th, 2023 3:00 p.m.
2023-10-11 | FRC INC | Please provide a copy of Attachment 3 to the RFP for the Lease-leaseback Contract and Preconstruction Services Agreement. | Will be provided once a succesful contractor is approved by District. | Wednesday, October 18th, 2023 3:00 p.m.
2023-10-11 | FRC INC | Please provide a copy of Attachment 4 to the RFP as noted on page 9. | Will be provided once a succesful contractor is approved by District. | Wednesday, October 18th, 2023 3:00 p.m.
2023-10-11 | FRC INC | Please confirm quantities of hard copies to submit as page 4 states one original and 3 hard copies and page 10 states one original and 4 hard copies. | One original, and 4 hard copies along with a digital copy (on a thumb drive) of the proposal must be submitted under sealed cover by no later than Due Date for Submittal of Proposals specified in Section III. | Wednesday, October 18th, 2023 3:00 p.m.
2023-10-11 | FRC INC | For Attachment 2 – Fee Proposal for Item #2 Lease-Leaseback Fee, does this include bonds and insurance? If so, does this include builders risk insurance? If builders risk insurance is to be included, please confirm if earthquake or flood insurance is required? | No, fee proposal will be lease-lease back fee. | Wednesday, October 18th, 2023 3:00 p.m.
2023-10-11 | FRC INC | For Attachment 2 – Fee Proposal, is there a financing component to the LLB Project? If so, are we to include a financing % as part of the Fee Proposal and if so in where? | No. | Wednesday, October 18th, 2023 3:00 p.m.
2023-10-11 | FRC INC | Is there a Phasing Plan that can be shared or an updated on the plan approval process for each location. | Will be in Pre-Construction Services. | Wednesday, October 18th, 2023 3:00 p.m.
2023-10-11 | Landmark | There is reference to building design, landscape design and site infrastructure design in the scope description on page 1 of the RFP. Can you please confirm whether we are to participate in design process? | Will be in Pre-Construction Services. | Wednesday, October 18th, 2023 3:00 p.m.
2023-10-11 | Landmark | Can you tell us which scope, if any, we would be able to complete during the school year? | Yes. Please see Pre-Construction Bid Walk Notes. | Wednesday, October 18th, 2023 3:00 p.m.
2023-10-11 | Landmark | Would you please post the handouts that were provided at the walks digitally? | See District Website. | Wednesday, October 18th, 2023 3:00 p.m.
2023-10-11 | Landmark | Page 4 states one (1) original and three (3) copes of the proposal. Page 10 states one (1) original and four (4) copies of the proposal. Can you please let us know how many copies the District would prefer for its review process? | One original, and 4 hard copies along with a digital copy (on a thumb drive) of the proposal must be submitted under sealed cover by no later than Due Date for Submittal of Proposals specified in Section III. | Wednesday, October 18th, 2023 3:00 p.m.
2023-10-11 | Landmark | Is the District able to share any project plans? | Refer to District Website. | Wednesday, October 18th, 2023 3:00 p.m.